July 24, 2012

Prop S Update

APPROVED AT SAB MEETING 07/10/2012

- Board Resolution #: 07-10-12-47 Flooring, Light Fixture Replacements & Painting @ Beaumont, Central VPA & Vashon

- Board Resolution #: 07-10-12-48 Kitchen Equipment Installation at Multiple Schools

- Board Resolution #: 07-10-12-49 Restroom Renovation – Category 3 & 4 at six (6) schools: Ashland, Buder, Hamilton, Henry, Oak Hill & Shaw

- Board Resolution #: 07-10-12-50 Painting at Gateway IT Aviation Garage

CONTRACTS SUBMITTED

- RFP #: PS21-1112 Early Childhood Classroom Furniture for Heritage Academy at Williams

- RFP #: PS38-1112 Restroom Renovations at Category 1 & 2 Schools at eight (8) schools: Central VPA, Cleveland, Mason, Mullanphy, Nottingham, Peabody, Walbridge & Woodward – 07/06/2012

- RFP #: PS39-1112 Restroom & Accessibility Update – Category 1 at four (4) high schools: Beaumont, Northwest, Roosevelt and Sumner – 07/10/2012

- RFP #: PS40-1112 Restroom Renovation – Category 3 & 4 at six (6) schools: Ashland, Buder, Hamilton, Henry, Oak Hill & Shaw

- RFP #: PS58-1112 Accessibility Update/Restroom Renovations – Category 1 at eight (8) schools: Busch, Carr Lane, Dewey, Humboldt, Long, Monroe, Stix and Woerner - 07/06/2012

- RFP #: PS62-1112 Access Road & Playground Lot Resurfacing & Playground Installation at Multiple Schools

- RFP #: PS64-1112 Health Clinic at Vashon High School – 07/09/2012

- RFP #: PS65-1112 Track Resurfacing of the Athletic Field @ Beaumont – 07/16/2012

- RFP #: PS67-1112 Flooring, Lighting and Painting @ Beaumont, Central VPA & Vashon – 07/20/2012

- RFP #: PS70-1112 Kitchen Equipment Installation @ Multiple Schools – 07/18/2012

- RFP #: PS72-1112 Painting @ Gateway IT Aviation Garage

BIDS BEING REVIEWED

- RFP #: PS71-1112 Fencing at Beaumont and Gateway High Schools

OUT FOR BID

- RFP #: PS75-1112 Playground Area Pavement Replacement and Walking Path @ Nottingham - 08/08/2012

RFP TO BE SUBMITTED FOR BID

- RFP #: PS37-1112 Painting and Flooring (Package 1) – 07/27/2012

- RFP #: PS56-1112 Electrical Upgrade Assessment by the ID/IQ Team – 07/27/2012

- RFP #: PS61-1112 IP Clock District Wide Schools – 07/27/2012

RFP UNDER CONSTRUCTION                        	Start	Substantial

Date	Completion

- RFP #: PS09-1011 Science Lab Renovations (Hankins)	10/26/2011	03/30/2012

- RFP #: PS09-1011 Science Lab Renovations (Midwestern)	11/21/2011	03/30/2012

- RFP #: PS17-1112 Athletic Field at Gateway	08/04/2011	12/14/2011

- RFP #: PS19-1112 PIIP Classroom Renovations	05/14/2012	07/31/2012

- RFP #: PS20-1112 Sumner Stair Tread Replacement	09/15/2011	02/28/2012

- RFP #: PS28-1112 Door Access & Security Alarm Upgrade	04/20/2012	10/16/2012

- RFP #: PS30-1112 Fire Alarm Upgrades	02/06/2012	08/19/2012

- RFP #: PS34-1112 Science Labs @ Nottingham	11/16/2011	01/31/2012

- RFP #: PS38-1112 Restroom Renovation - Category 1 & 2	07/02/2012	08/13/2012

- RFP #: PS39-1112 Restroom & Accessibility Update Category 1	07/02/2012	10/31/2012

- RFP #: PS40-1112 Restroom Renovation - Category 3 & 4	07/31/2012	07/31/2013

- RFP #: PS41-1112 Culinary Kitchen @ Beaumont	02/20/2012	06/30/2012

- RFP #: PS44-1112 Waterproofing, etc. @ Mullanphy	02/06/2012	05/29/2012

- RFP #: PS45-1112 Greenhouse Renovation @ Gateway IT	03/15/2012	07/31/2012

- RFP #: PS53-1112 Window A/C Unit Installations @ Gateway IT	04/20/2012	07/05/2012

- RFP #: PS54-1112 Waterproofing, etc. @ Multiple Schools	05/29/2012	01/05/2013

- RFP #: PS55-1112 Health Clinic at Roosevelt	06/21/2012	08/11/2012

- RFP #: PS58-1112 Accessibility Update/Restroom Renovations	07/02/2012	08/13/2012

- Design Phase

  - ADA (Americans with Disabilities Act): Review being coordinated with the City of St. Louis.  Permits for demolition and construction are being delayed until this is completed at each SLPS property.  This will delay completion schedule.

  - Health Clinic @ Vashon: Final design for this project is being developed for approval.

- Abatement Phase

  - Program analysis is ongoing for the Lead Abatement Program.  Lead interim controls were completed at seven (7) schools over the spring break.  The schools are: Dewey, Ames, Mann, Sherman, Shenandoah, Washington Montessori, and Woodard.

  - Program analysis is ongoing for the Restroom Renovations.

  - Hazmat activities continue in support of the Tuckpointing Renovation Projects.

  - Abatement activities are scheduled to begin for the mechanical modernization program at Buder Elementary.

  - Abatement activities are scheduled to begin for the mechanical modernization program at Mallinckrodt Elementary.

  - Abatement activities are scheduled to begin for the Cafeteria/Auditorium window project at Central VPA High School.

  - Abatement activities are scheduled to begin for the mechanical retrofit project at Gateway High School.

  - Hazmat activities are 70% complete at the Former Hodgen School.

- Construction Phase

- PS03-1011 Kitchen Equipment @ Central VPA Servco has mobilized and started installing their walk-in cooler and walk-in freezer and associated refrigerant piping.  This installation is scheduled to be completed the week of July 23, 2012.  Servco is scheduled to set all of the remaining equipment the week of July 30, 2012.

- PS04-1011 Portable & Mobile Radios the problem with Warner Communications System is not fully resolved to insure the system functions in accordance with their bid.  A plan is being developed to install a Radio Tower on SLPS property.

- PS09-1011 Science Lab Renovations - Team A (Midwestern) the contractor has installed their first coat of paint on the walls.  They have started installing the casework, countertops and backsplashes.  Once casework and countertops are installed, Midwestern will apply their final coat of paint followed by the floor installations.  The Gateway IT science lab is scheduled to be completed by the end of August 3, 2012.

- PS09-1011 Science Lab Renovations - Team B (Hankins) is substantially complete.

- PS10-1011 Roofing Work new installation, renovation and spot repair of district properties is ongoing at: Bryan Hill, Cote Brilliante, Farragut, Food Services, Gateway Elementary, Kennard, Kottmeyer, L’Ouverture, Mallinckrodt, Nottingham and Oak Hill.

- PS17-1112 Athletic Field at Gateway City code required ADA upgrades and new shot put area work has started.

- PS19-1112 PIIP Classroom Renovations the contractor is continuing work at both Sumner and Roosevelt High School.

Roosevelt PIIP: The contractor has installed their drywall and started their taping scope of work.  There have been minor delays with the taping portion of work due to the A/C being turned off occasionally.  They received their casework and are scheduled to begin installation following wall finishes.  The Roosevelt PIIP project is scheduled to be complete on/or before August 10, 2012.

Sumner PIIP:  The contractor has completed their wall finishes and started their casework and countertop installations.  They have installed the ceiling grid and lay-in fixtures.  The Sumner PIIP project is scheduled to be complete on/or before August 10, 2012.

- PS20-1112 Sumner Stair Treads is substantially complete with the exception of some stair tread and handrail rework in one stairwell.  This work is scheduled for completion by August 10, 2012.

- PS26-1112 RE4 Boxes – Package 3 the contractor mobilized and completed their work at Cote Brilliante and Bryan Hill.  They are expected to complete their work at Clay the week of July 23, 2012.  They are also expected to mobilize and start their work at Farragut the week of July 23, 2012.  This scope of work is scheduled to be completed by August 10, 2012.

- PS28-1112 Door Card Access & Security Alarm System Upgrade

Painting: ADT has mobilized and completed their painting portion of work at Ames, Madison, Beaumont, Clay, Froebel, Walbridge, Cote Brilliante, Woodward, Dewey, Peabody, Shenandoah, Langston, Cole, Lyon, Sherman, Dunbar and Mullanphy.

Monitoring System/Door Access: ADT has installed their monitoring system at Langston for approval.  Pending approval, they are scheduled to mobilize the week of July 23, 2012 to start installing their door card access system at Nance, Herzog and Lexington.  Approval granted and work is underway.

Doors: This portion of work is scheduled to begin late summer 2012.

- PS30-1112 Fire Alarm Upgrades the contractor is scheduled to complete the rough-in work at Lexington, Fanning, Woerner, Peabody, Sigel, Columbia and Ames mid July 2012.  The rough-in work at Sumner is scheduled to continue through late July 2012.  All final connections and change over work is expected by late July 2012.  This scope of work is scheduled to be complete by August 10, 2012.

- PS32-1112 Window Shades – Package 4 Huffman is substantially complete with the shade installations at Long Middle, Adams Elementary, Kennard Elementary, Wilkinson @ Roe and Kottmeyer.

- PS34-1112 Nottingham Science Labs work continues.  The contractor started some of their furniture and finish installations.  The wall finishes are complete and casework installation is complete with the exception of the replacement of a countertop that was damaged during delivery.  This scope of work is expected to be ready for punchlist the week of July 30, 2012 and final completion by August 10, 2012.

- PS36-1112 Old Hodgen Demolition work is underway 25% complete.

- PS38-1112 Restroom Renovation – Category 1 & 2 Schools the work at Nottingham and Mullanphy are scheduled to be complete by August 10, 2012.  The contractor is about 90% complete with the demolition work.  They have also started their plumbing rough-in work at all of the schools.  All other schools are scheduled to be completed by the end of August 2012.

- PS41-1112 Beaumont CTE Culinary Kitchen the contractor has completed the drywall, taping, and FRP (Fire Resistance Plastic) installations and wall finishes.  They have installed their hood and associated ductwork.  The contractor installed quarry tile throughout the space and are scheduled to begin setting food service equipment late July 2012.  This work is scheduled to be completed the week of August 13, 2012.

- PS44-1112 Waterproofing, Tuckpointing & Plastering at Mullanphy the contractor has completed the tuckpointing, roofing and waterproofing scope of work.  They have backfilled the perimeter walls and seeding/sod work is scheduled following the extreme temperatures.  They have completed their ceiling tile and fixture installations and flooring.  This scope of work is scheduled to be complete by early August 2012.

- PS45-1112 Greenhouse Renovation @ Gateway IT this contractor has mobilized and completed the demolition of the existing steam lines.  The contractor has installed all required framing and panels at the front wall.  They have also started to install framing in preparation of the roof panel installations.  They will continue with the electrical rough-in work the week of July 23, 2012.  This scope of work is scheduled for an early August 2012 completion.

- PS47-1112 Central VPA Kitchen and Auditorium Renovations the contractor removed the entire scaffold from the auditorium and installed the new concrete floors.  They have also completed all of the ceiling work including their painting, mechanical and electrical rough-ins and perimeter walls installations and painting.  The contractor continues their wall and floor finishes in the auditorium.  They are expected to install the new roof top units early August 2012 as well as their auditorium seating.  The contractor has also completed the metal stud and in wall and underground rough-in work in the kitchen as well as their drywall and taping work.  They have installed some of the epoxy floors in coordination with the walk in cooler and walk in freezer installations.  Finishes are expected to begin early August 2012.  The kitchen scope of work is expected to be complete by August 10, 2012 and the auditorium work is expected to be complete by mid September 2012.

- PS50-1112 Refinish Gym Floors at Gateway and Soldan the contractor has mobilized and sanded the flooring and replaced wood flooring as required.  They have started installing stain at Soldan and are schedule to start their stain installation at Gateway the week of July 23, 2012.  The floor painting is scheduled to begin late July 2012.  This overall scope of work is scheduled to be complete by August 10, 2012.

- PS51-1112 Project Site Signs the contractor has mobilized and installed the sign at Sumner High School.  All other schools are on hold pending the sign development at each school.  This work was originally scheduled for completion in the spring of 2012.

- PS53-1112 Gateway IT Window A/C Unit Installations the contractor has mobilized and completed their bus duct portion of the work.  The new power system for the window units is expected to be operational the week of July 23, 2012.  The rough-in work is about 90% complete and wire has been pulled on the fourth floor.  The contractor has started pulling wire on the third floor.  The contractor has started reworking the window and installing window units on the fourth floor.  This scope of work is scheduled to be complete by August 10, 2012.

- PS54-1112 Waterproofing, Tuckpointing and Plastering at Multiple Schools the contractor has mobilized and started their mortar mock up work at Clay Elementary, McKinley High, Soldan High, Mann Elementary, Mason Elementary, Mallinckrodt Elementary and Buder Elementary.

Buder: The contractor has completed about 90% of the tuckpointing and joint caulking portion of work.  In addition, they are about 5% complete with the plaster and painting portion of work.

Clay: The contractor has completed about 25% of the tuckpointing and joint caulking portion of work.  In addition, they are about 10% complete with the plaster and painting portion of work.

Mallinckrodt: The contractor has completed about 90% of the tuckpointing and joint caulking portion of work.  In addition, they are about 5% complete with the plaster and painting portion of work.

Mann: The contractor has completed about 95% of the tuckpointing and joint caulking portion of work.  In addition, they are about 75% complete with the plaster and 10% painting portion of work.

McKinley: The contractor has completed about 50% of the tuckpointing portion of work.  In addition, they are about 5% complete with the plaster portion of work.

Soldan: The contractor has completed about 10% of the tuckpointing and joint caulking portion of work.  In addition, they are about 5% complete with the plaster and painting portion of work.  The contractor has also started their waterproofing excavations.

- PS55-1112 Health Clinic at Roosevelt the contractor has installed drywall and tape in most areas of the health clinic.  They are expected to begin finishes late July 2012.  This project is expected to be completed by August 13, 2012.

- PS58-1112 Restroom & Accessibility Update Category 1 Schools the contractor is about 90% complete with the demolition work.  They have also started their plumbing rough-in work at all schools.  The work included in this scope is scheduled to be complete by September 2012.

- PS62-1112 Access Road & Playground Lot Resurfacing & Playground Installations the contractor has mobilized and started their playground, fencing, asphalt and tree demolition work at schools as required.  Their asphalt paving work is scheduled to be completed by early August 2012.  The playground ship dates are still be determined.