## 06 19 13
| Action Steps | Start Date | End Date | 25% Benchmark (BM1) | 50% Benchmark (BM2) | 75% Benchmark (BM3) | 100% Benchmark (BM4) | Completion / Evidence | % Progress toward Benchmark Attainment |  |  |  | Owner | Cross-Reference
I | 1. Student Performance
I | GOAL: To achieve full accreditation by receiving the necessary point as determined by MSIP 5. | [7 empty] | BM1 | BM2 | BM3 | BM4 | Team Leader: Nicole Williams
I.A | Objective A: The District will provide the necessary resources to ensure all SLPS students perform at/above grade level in reading and math and significantly improve instructional effectiveness as evidenced by improved student performance. | 2011-07-01 | 2013-06-30 | Establish benchmark assessment baselines | Acuity/Edmin Benchmark - Attain 10% increase over baseline | Acuity/EdminBenchmark - Attain 20% increase over baseline | Submittal of Completion of Evidence | The Accountability Office completed an analysis that documented the statistical alignment (relationship)between the high school benchmarks and the EOC’s (filed on the Accountability L drive). The test vendor, CTB McGraw-Hill provided a copy of their 2012 Technical Summary that documented the alignment of the Acuity benchmarks to the MAP. All schools were provided with baselines from which to set targets. | 100% | 100% | 100% | 100% | Nicole Williams; Cleopatra Figgures | CSIP 1-15, 17-23,25 MSIP 6.1, 6.3 6.5, 1.3, 9.1, 6.3 CLRP: 1, 4, 12, 14, 19, 20, 21, 22, 24, 25, 26, 30
I.A.1 | Strategy 1:Ensure that all students receive differentiated, relevant, and rigorous instruction through the SLPS Literacy Model | 2012-07-01 | 2013-06-30 | Develop the SLPS Literacy Model and share with teachers, receive feedback, refine and publish. Distribute the model through the Academic Team | Develop an implementation plan and devise roll out plan for professional develoment and coaching through AICs and the Academic Team | Document the use of the SLPS Literacy Model, PK-12, in every school by every classroom teacher as evidenced through lewsson plans and Focused Instructional Learning Walk | Submittal of Completion of Evidence | SLPS Literacy; Focused Instructional Learning Walk data indicates that all classroom teachers are implmenting the agreed upon components of the SLPS Lteracy Model to ensure rigorous and relevant instruction | 100% | 100% | 100% | 100% | Sheila Smith Anderson | CSIP: 1 ,2, 18-20, 23, 36, 50, 55, 61, 63 MSIP: 9.1, 6.3.1, 6.3.3, 6.7.2, 6.7.4, 6.9.3, 7.6.1 CLRP: 1, 3, 14, 16, 18, 19, 22, 30
I.A.I.a | Develop district-wide plan professional development to support the implementation of the SLPS Literacy Model | 2012-10-01 | 2013-06-30 | District-wide professional development plan is designed to introduce components of the SLPS Literacy Model focusing on academic vocabulary, word walls, and anchor charts | District-wide profesional development plan is designed with sessions focusing on text-based discussions, wide reading, and citing evidence in various output formats (presentations, debates, etc.) to further expand implentation of the district-wide professional development SLPS Literacy Model | District-wide professional development sesions designed focusing on writing to learn across content to suppport the SLPS Literacy Model | Submittal of Completion of Evidence | My Learning Plan, Professional Development offerings, student work, and lesson plans | 100% | 100% | 100% | 50% | Sheila Smith Anderson;
I.A.I.b | Support staff in implementing well researched best practice, supplementary, alternative literacy and math strategies for Tier II & III interventions. | 2012-11-01 | 2013-06-30 | Support the school's Rtl Plan to Idnetify district-supported instructional strategies for communications arts and math literacy for Tier II and Tier III interventions | Integrate District PD to support interventions through development for bilding level Rtl leadership team and staffs. | Assess impact of professional develoment on classroom instruction through, PD committees and surveys | Submittal of Completion of Evidence | Dat, including the high Rtl Rubric, intervention data, Focused Instructional Walk data | 100% | 100% | 100% | 100% | Sheila Smith Anderson
I.A.1.c | Design, train/support staff and implement a tiered model of intervention across all K-8 school sites | 2011-09-01 | 2012-06-30 | Develop a PD plan for RtI implementation for school based teams for the purpose of transferring RtI into the classroom as evidenced by agendas and plans. | Assess the level of implementation of the school level RtI plan through quarterly meetings with the members of the teams as evidenced by rosters, agendas, and minutes | Assess the use of EdMin with IAPs as of January 2012 to June 2012 to determine level of interventions in place for struggling students | Submittal of Completion of Evidence | Implement PD plan; conduct program evaluation to determine effectiveness |  |  |  |  | Sheila Smith Anderson
I.A.I.d | Monitor the progress and provide supports for students who are reading below grade level and provide appropriate wraparound services | 2009-09-08 | 2013-06-30 | Establish processes to identify students reading below grade level | Implement RtI model for intervention; determine if additional resources and supports are needed beyond academic support | Provide evidence of collaboration between counselor and classroom teacher of any home and or additional community resources needed for support beyond academics | Submittal of Completion of Evidence | Provide documentation that identifies students' progress and show evidence of monthly reviews by the building SIT team | 80% | 75% | 75% |  | Chip Jones; Sheila Smith Anderson
I.A.I.f | Refine and train/support staff in the CARE/Student Intervention Team process | 2009-08-01 | 2013-06-30 | Determine appropriate SIT team membership, roles and responsibilities by Spring of 2009 | Design group processes by which each team operates in line with PLC guidelines and the program evaluation to determine effectiveness Spring of 2011 | - Design and implement professional development plan and implement SIT teams in each building across the district by June 2013 | Submittal of Completion of Evidence | CARE & SIT teams are initiated | 100% | 100% | 90% |  | Chip Jones
I.A.I.h | Audit master schedules in every school to ensure occurrence of appropriate and viable course offerings with the number of minutes per the state standards | 2012-08-01 | 2013-06-30 | Design a process for examining master schedules to determine gaps | Examine master schedules and report on discrepancies by school | Convey information to principals regarding discrepancies with a timeline for remediation | Submittal of Completion of Evidence | All schools' master schedules for the 2012-2013 school year will reflect appropriate course offerings with correct number of minutes | 100% | 100% | 100% | 100% | Paula Knight; Dan Edwards; Rosemary Martin; Sheila Madkins
I.A.2 | Strategy 2:Provide data to increase the number of students scoring at proficiency or above in Math and Communications Arts for all subgroups to meet state requirements for AYP | 8/20/2011 | 2013-06-30 | Create data tool and form showing benchmarks and targets of students for each school | Provide data to schools and Central Office staff | Continuously update data on tool (PULSE) and in information provided to schools | Data updated on PULSE | Review of actions indicates all targets are met for 2012. Introduced new MSIP 5 accountability process to all schools. Provided MSIP 5 data to schools. | 100% | 100% | 100% | 100% | Bertha Doar; Cleopatra Figgures | MSIP: 6.2, 6.3, 6.4, 7.1, 9.1, 9.2, 9.3 CSIP: 18-20, 23, 36, 50, 55, 61, 63 CLRP: 1, 14, 16, 18, 19, 22, 30
I.A.2.a | Ensure staff are trained in MAP instructional strategies including creating, using and scoring MAP-like assessments throughout the year. | 2012-11-30 | 2013-06-30 | Audit current work, design a data tool; conduct PD for ongoing, rotational sessions. | Develop process to enusre the dicsrepancies and ideal model(s) are addressed. | All sessions occuring through planned PD sessions. | Submittal of Completion of Evidence | All sesions completed prior to MAP testing; additionally introduced new accountability structure to schools. | 100% | 100% | 100% | 100% | Bertha Doar; Cleopatra Figgures
I.A.2.b | Monitor the instructional frequency of Grade Level Expectations/Content Level Expectations (GLEs/CLEs) through lesson plan design, using an electronic tool | 2011-09-01 | 2013-06-30 | - Identify a resource/consultant to electronically collect GLE/CLE frequency use – December, 2011 | Develop a process / programming tool to track GLE/CLE use in lesson plans; identify baseline of GLEs/CLEs addressed – June 2012 | Train all staff in use of data collection process/instrument – June 2012 | Submittal of Completion of Evidence | Report indicates 50% of GLEs/CLEs are addressed in lesson plans-December, 2013 | 100% | 100% | 100% | 100% | Sheila Smith Anderson
I.A.2.d | Revise the Individual Academic Plan (IAPs) model, structuring a team (Content Area Specialist, Teaching Learning Facilitator (TLFs) and selected district personnel) to collaborate on creating exemplar intervention modules for deficient academic areas and exemplar IAPs based on benchmark assessments, teacher-made assessments and analysis of MAP. | 2011-09-08 | 2013-06-30 | - Develop a plan to establish and revise the process for IAP review and revision and monitoring; schedule in teacher-made assessments and lesson plan | - Design and Pilot the IAP process, February 2013 | Refine the IAP based on pilot feedback, implement with in pilot schools and develop a plan for expanding the revised IAP pilot, June 2013 | Submittal of Completion of Evidence | Revised IAP, and Plan for expanding the | 100% | 50% | 0% |  | Chip Jones, Bertha Doar, Sally Walser, Joshua Kurth, Pauline Moley, Sheila Smith Anderson Cathy Cassy, Kathleen Taggart, and Paula Knight
I.A.3 | Increase the number of students in K-8 reading and math at grade level or above by 10% | 2012-11-30 | 2012-06-30 | Revise and update the Individual Academic Plan and post to Curriculum and Instruction website | Develop Individual Academic Plan/Individual Reading Plan for all students scoring 1 or more years below grade level for K-8 students by the middle of the second quarte | Assess, review and revise plans by the middle of the 3rd quarter analyze the GLE/CLE addressed through IAPs; report to PLC teams and PD comm. for use in district p.d. planning. | Submittal of Completion of Evidence | IAP’s on file at the schools; review of committee findings and recommendations to the Academic Office for changes in instructional processes/offerings/interventions | 100% | 100% | 100% | 100% | Sheila Smith Anderson;Paula Knight; Dan Edwards, and Rosemary Martin
I.A.3.b | Provide teachers with the Common Core State Standards sample intrructional teaching strategies in relationship to District IBD analysis | 2012-12-14 | 2013-06-30 | Develop a timeline for the distribution of instructional strategies samplers and exemplars from CCSS | Teafhers use the CCSS strategies and exmplars in lesson plan design as evidenced through (Focused) Instructional Learning walks | Teachers share lessons developed using CCSS and research based strategies via C & I website and school protals | Submittal of Completion of Evidence | Focused Instructional Learning Walk data; strategies posted on the C&I website | 100% | 100% | 100% | 100% | Sheila Smith Anderson
I.A.3.d | Ensure all elementary and middle school sites offer academic after school programs to provide extended day experiences | 2012-10-05 | 2013-06-30 | Audit locations and types of current after school programs on a quarterly basis | Establish desired after school program parameters to be addressed at all school sites prior to opening of school. Monitor on a quarterly basis. | Determine gap between existing and desired programming parameters prior to opening of school. Monitor on a quarterly basis. | Submittal of Completion of Evidence | Provide evidence of plan development and implementation that ensure all school sites have optimum after school programming by Sept 2013. Generate EOY Report and present to SAB @ October 2013 Bd Mtg. | 100% | 100% | 100% | 25% | John Windom; Judith King
I.A.4 | Strategy 4:Align all district assessments with district curricula and focus on using results to inform instruction and improve overall student and district performance | 2011-08-20 | 2013-06-30 | Update a plan to implement benchmark and targets set for action steps of Strategy 4 | Review plan to determine if benchmarks indicated in plan are met @ 50% level | Review plan to determine if benchmarks indicated in plan are met @ 75% level | Submittal of Completion of Evidence | Review of Plan indicates targets were met. | 100% | 100% | 100% | 100% | Bertha Doar; Cleopatra Figgures | MSIP: 6.1, 6.2.1, 6.2.3, 6.2.4, 6.3, 6.3.4, 6.5.2, 6.7.2, 9.1, 9.1.2, 9.1.3 CSIP: 1, 27, 29-34 CLRP: 3, 30
I.A.4.a | Review and refine the number of formal benchmark assessments and ensure they are aligned to the pacing guides. | 2011-08-20 | 2013-06-30 | Create team to examine current formal benchmark assessments used in SLPS | Determine current alignment with SLPS core curricula and pacing guides | Adjust comprehensive assessment plan | Submittal of Completion of Evidence | Comprehensive assessment plan was integrated into 2012-2013 School Calendar; posted on website; disseminated to all schools. | 100% | 100% | 100% | 100% | Bertha Doar; Cleopatra Figgures
I.A.4.b | Develop a plan for the distribution and use of data in a usable format specific to each school site and usable by the administration and school leadership team for instructional decision making to increase student achievement | 2011-08-30 | 2013-06-30 | Determine data desired and needed by school sites | Examine current available data to determine alignment with articulated desires and needs | Review and update current data dissemination process and data management tool | Submittal of Completion of Evidence | Data Management Tool is operational for all Schools | 100% | 100% | 100% | 100% | Bertha Doar; Cleopatra Figgures
I.A.4.c | Develop and implement processes to ensure alignment between curriculum, assessment and professional development. - Assessment Office staff will facilitate work with Curriculum and teachers to re-align key hs benchmarks this summer based on results suggesting possible need. PD planning is ongoing. | 2012-10-05 | 2013-06-30 | Establish system of meeting with Curriculum and Instruction team on a bimonthly basis and schedule as an agenda item; add professional development sessions to address the – provide agendas through June 2013 | Address non-alignment issues on a monthly basis | Regularly schedule team meetings to determine if plan is successful in addressing identified alignment issues - provide agendas through June 2013 | Submittal of Completion of Evidence | Provide evidence via a random survey that alignment between curriculum, assessment and professional development exists | 100% | 100% | 100% | 90% | Bertha Doar, Sheila Smith Anderson, Audrey Jackson
I.A.4.d | Create a user's guide to assessment that explains the purpose for formative assessment and suggests protocols for using data from the assessments | 2011-10-12 | 2012-06-30 | Create team to develop user's guide to assessment | Develop table of contents and format for guide | First draft of guide was completed and disseminated to random vertical groups for review and feedback | Submittal of Completion of Evidence | Distribute completed guide to staff via scheduled professional development . Gudie must be realigned to CCS and MSIP 5 structure | 50% | 50% | 75% |  | Bertha Doar; Cleopatra Figgures
I.A.5 | Strategy 5: Ensure that the guidance and gifted curricula and supporting documents are aligned to state standards and grade or course level expectations | 2011-08-20 | 2012-11-07 | Design and begin implementation of a plan to action steps of Strategy 5 | Review of plan indicates benchmarks and targets indicated in plan are met at 50% level | Review of plan indicates benchmarks and targets indicated in plan are met at 75% level | Submittal of Completion of Evidence | Review of plan indicates targets are met | 100% | 100% | 100% |  | Chip Jones | MSIP: 6.1, 6.1.1 CSIP: 51
I.A.5.a | Ensure that the curriculum and its supporting documents are aligned Common Core Standards | 2013-01-04 | 2013-06-30 | Identify teams to review curriculum; include specialists, regular and gifted education teachers | Teams review existing curriculum to ensure documents are in alignment with state standards and Common Core Standards by April 2013 | Team to ensure that curriculum embeds gifted curricula in the four core subject areas in grades PK-12 that embeds Common Core Standards | Submittal of Completion of Evidence | Provide evidence of curriculum review that shows embedded guidance and gifted items in curriculum based on Common Core Standards by June 2013 | 50% | 50% | 50% | 50% | Sheila Smith Anderson
I.B.1.a | Provide End of Course (EOC) data to teachers and Teaching Learning Facilitators (TLFs); determine and target CLEs necessary for focused and targeted interventions | 2009-08-31 | 2013-06-30 | Create team (include classroom teachers), to design a plan to include assessing schools not in receipt of PLC training and PD for developing aligned teacher made tests and formative assessments | Share proposed plan with schools for feedback, including a timeline for training with topics, dates, presenters and formative assessment loops for adjustment | Begin implementation of plan in Spring 2010 with formative assessment loops driving refinement for 2010-2011 school year. Alignment was completed. Determination of EOC scores will not be available until July 2013. | Submittal of Completion of Evidence | A fully developed plan will be implemented in 2010-2011 and 2012 - 2013 school years | 100% | 100% | 100% | 100% | Cleopatra Figgures; Bertha Doar; Dan Edwards; Sheila Smith Anderson; Pauline Moley; Nicole Williams
I.B.2 | Strategy 2: Ensure that all high schools offer career and technical courses that have an identified set of learning experiences. | 2009-09-14 | 2012-09-30 | Conduct audit and design a process to ensure consistent course offerings across school sites | Provide evidence that 50% of schools have consistent course offerings across schools | Provide evidence that 75% of schools have consistent course offerings across schools | Submittal of Completion of Evidence | Provide evidence that all high schools have consistent course offerings across schools | 100% | 100% | 100% | 100% | Tim Murrell | MSIP: 6.1, 6.2, 6.3 CSIP: 5, 39, 147 CLRP: 4, 26
I.B.2.a | Conduct an external audit of course offerings to ensure appropriate career education offerings and students' equitable access to technology and instructional resources | 2011-09-14 | 2012-06-30 | Provide evidence of the audit of current course offerings and access opportunities | Determine gaps in existing offerings, opportunities and desired state | Develop plan to address gaps between current state and desired state | Submittal of Completion of Evidence | Information provided by the report from a third-party auditor, as required by the Carl D. Perkins grant. | 100% | 100% | 100% | 100% | Tim Murrell; Sheila Madkins; Sheila Smith-Anderson’s
I.B.3 | Strategy 3: Increase the number of students scoring at or above the national average on the ACT. | 2011-09-14 | 2012-06-30 | Design and implement plan for attaining benchmarks and targets for action Step 1.B.3.c | Review plan and establish attainment of benchmark at 50% level | Review plan and establish attainment of benchmark at 75% level | Submittal of Completion of Evidence | Data show continued improvement in average ACT scores. Revisions were made to align to MSIP 5 standards. | 100% | 100% | 100% | 100% | Bertha Doar; Sally Walser; John Niemeyer; Paula Knight; Dan Edwards; Rosemary Martin; Nicole Williams
I.B.3.c | Provide additional opportunities for student to have access to ACT Preparation Courses and/or study sessions | 2011-09-08 | 2013-06-30 | Audit current opportunities for student access to ACT preparation courses and/or student sessions | Determine gaps between current opportunities and desired opportunities | Develop process to address gaps between current and desired opportunities for students | Submittal of Completion of Evidence | Data show continued improvement in average ACT scores. Revisions were made to align to MSIP 5 standards. | 100% | 100% | 100% | 100% | Bertha Doar; Cleopatra Figgures; Dan Edwards
I.B.7 | Strategy 7:The District will provide internship experiences and industry certifications, where applicable, for students in career and technical programs. | 2011-09-08 | 2013-06-30 | Design a plan to increase internships/ partnerships | Provide documentation that Internships/partnerships have increased by 10% throughout the District | Provide documentation that industry certifications have increased by 5% throughout the District | Submittal of Completion of Evidence | Provide evidence that the participating schools have an increase in partnerships/ internships at the 10% level or above | 100% | 100% | 100% | 100% | Tim Murrell | MSIP: 7.3.2, 7.3.3, 7.6.1 CSIP: 38, 39, 41 CLRP: 4
I.B.8.c | Work with community and business sector to identify mentors for students at risk of dropping out of high school | 2011-06-15 | 2013-06-30 | Schools monitor screening process to identify potential dropouts on quarterly basis | Schools compile quarterly roster of potential dropouts to develop IAP 's for Bldg. Admin to implement | Schools work with community partners to identify sufficient pool of mentors to support all students on quarterly basis | Submittal of Completion of Evidence | Principals provide documentation to the Office of Institutional Advancement (OIA) that all students are assigned to mentors; with consideration made to match for industry interest and personality compatibility. OIA will generate EOY report and present to SAB @ July 2013 Board Meeting | 47% | 47% | 47% | 47% | Debra Falkiner; Blake Youde, Charlie Bean, John Niemeyer, Paula Knight, Dan Edwards, Rosemary Martin, Principal
I.B.9 | Strategy 9: E: Ensure processes are in place to support at risk students with programs to deter dropping out from school and providing additional services to recover those who have dropped out from school. | 2011-06-12 | 2013-06-30 | Identify students at risk of dropping out or have already dropped out by using available databases by designated building problem solving teams and district support services. | - Provide interventions for those students at risk of dropping out or have already dropped out by designated building problem solving teams and district support services. | Monitor students at risk of dropping out or recovered drop outs by designated building problem solving teams and district support services. | Submittal of Completion of Evidence | Completion of program will be evidenced by a final report by June 30, 2013. | 100% | 100% | 100% | 100% | Owner(s): Debra Falkiner : Support Charlie Bean, John Niemeyer, Chip Jones, Ira Biverns, Megan Marietta, Richelle Clark: Consultants: Paula Knight, Rosemary Martin, Dan Edwards | MSIP 9.5
I.B.10.a | Monitor and document the progress of seniors as they apply to postsecondary programs or institutions of higher education | 2011-09-01 | 2013-06-30 | Review and revise processes to determine post graduate plans and monitor goal attainment for all high school seniors across 2011-12 school year | 50% of seniors will have applied to at least one postsecondary programs or institutions of higher education by the end of first semester | 85% of seniors will have applied to at least one postsecondary programs or institutions of higher education by the end May 2013 | Submittal of Completion of Evidence | CSNAV Yearly Report May of 2013 as evidence of senior that apply to post secondary programs or institutions of higher education. | 100% | 100% | 70% |  | Chip Jones
I.B.10.b | Provide postsecondary planning courses for students and provide training for teachers to teach the courses | 2009-09-08 | 2012-08-30 | Create team, (include HS principals); assess current state of existing courses; design plan for inclusion in buildings identified as in need; design PD plan for teachers during the Spring of 2011 | Conduct training for teachers in Fall of 2011 and Spring of 2012 | Ensure inclusion of courses in the 2013 HS master schedules by August 30, 2012. | Submittal of Completion of Evidence | Program /outcome data and training agendas, College Summit Courses placed in the 2012-13 High School master Schedules. | 100% | 100% | 100% |  | Chip Jones
I.B.11.a | Implement a 4-year electronic graduation plan at the end of 8th grade. | 2009-08-01 | 2013-11-07 | Explore electronic plans for tracking student progress Fall 2009 | - Select and develop plan for tracking student progress to graduation 2010-11 | Implement the electronic 4 year planning process across the 2011-12 and 2012-13 school year | Submittal of Completion of Evidence | Provide evidence that tracking plan was implemented | 100% | 100% | 50% |  | Chip Jones
I.D | Objective D: Increase the learning of students for special education and ESOL students. | 2009-07-01 | 2013-06-30 | Design and implement plan for addressing action steps of Objective D | Review of plan indicates benchmarks established are met at 50% level | Review of plan indicates benchmarks established are met at 75% level | Submittal of Completion of Evidence | Review of plan indicates benchmarks and targets are met | 100% | 100% | 100% | 100% | Nahed Chapman; Michael Haggen; Sheila Smith Anderson | MSIP: 6.1, 6.2, 6.2.2, 6.3.1, 6.3.3, 8.1.1 CSIP: 17-20, 22, 23 CLRP: 1, 14,18, 22, 30
I.D.1 | Strategy 1: Design/Expand, train staff and implement options for special education services in the least restrictive environment. | 2009-08-01 | 2013-06-30 | Design and implement plan for addressing action steps of Objective D across 2009-13 school years | Review of plan indicates benchmarks established are met @ 50% level across 2009-13 school years | Review of plan indicates benchmarks established are met @ 75% level across 2009-13 school year | Submittal of Completion of Evidence | Review of plan indicates benchmarks and targets are met | 85% | 50% | 30% |  | Chip Jones
I.D.I.a | Include special education teachers in training for general education and provide specific training for specialized/gap areas | 2009-08-01 | 2013-06-30 | Ensure district wide professional development calendar includes SPED specific PD across the 2010-13 school years | Design training for specialized/gap areas 2009-13 school years | - Implement training for specialized/gap areas across 2009-13 school years | Submittal of Completion of Evidence | Include specifics as part of implemented district-wide professional development plan | 75% | 75% | 75% |  | Chip Jones; Audrey Jackson
I.D.2 | Strategy 2: Revise the ESOL instructional program to improve performance and enable English Language Learners to meet their academic and career goals. | 2011-08-01 | 2012-12-30 | Design and implement plan for addressing action steps 1.D.2.a - 1.D.2b | Review of plan indicates benchmarks established are met at 50% level | Review of plan indicates benchmarks established are met at 75% level | Submittal of Completion of Evidence | Review of plan indicates benchmarks and targets are met | 100% | 100% | 100% | 100% | Nahed Chapman; Dan Edwards, Paula Knight; Chip Jones,; Michael Haggen; Sheila Smith-Anderson | MSIP: 2.1.1, 6.1.1, 6.2, 6.3, 6.5.4, 7.5.1, 8.8.1, 8.8.2 CSIP: 64-69 CLRP: 13
I.D.2.a | Revise ELL instructional delivery plan to align with WIDA standards and ACCESS assessments | 2011-08-01 | 2012-12-30 | Train ESOL teachers and administrators on interpreting ACCESS scores to design aligned instructional delivery | Pilot new instructional delivery plan | Review feedback, finalize plan and monitor implementation | Submittal of Completion of Evidence | Document professional devleopment on interpreting ACCESS scores, design of instructional plan and implementation of plan | 100% | 100% | 100% | 100% | Nahed Chapman
I.D.2.b | Provide ELL professional development to support new instructional delivery plan | 2009-08-01 | 2014-06-30 | Design effective professional development , namely Sheltered Instruction Observation Protocol (SIOP) to support the instructional delivery plan | Implement SIOP professional development, cohort I, 2009 - 2011, for elementary and high schools | Expand SIOP training, cohort II, to include middle schools, 2011-2014 | Submittal of Completion of Evidence | Review professional development plan indicates targets are met | 100% | 100% | 100% | 100% | Nahed Chapman
I.D.2.c | Increase services and opportunities for English to Speakers of Other Languages ESOL parents to be engaged in the educational and social life of the school | 2009-08-01 | 2014-06-30 | Conduct comprehensive needs assessment, including survey and focus groups with parents of ESOL students to determine needed services and opportunities to engage them in school life | Develop plan to increase services and opportunities to engage parents of ESOL students in the educational and social life of the school | Create review panel of educators and parents of ESOL students to determine viability of proposed plan | Submittal of Completion of Evidence | Provide evidence of an implemented plan | 100% | 100% | 75% |  | Nahed Chapman
I.D.3 | Strategy 3: Develop processes and protocols within schools to reduce barriers to education for children and youth experiencing homelessness. | 2011-08-01 | 2012-11-30 | Monitor the plan for addressing action steps of Strategy 3 | Review of plan indicates benchmarks established are met @ 50% level | Review of plan indicates benchmarks established are met @ 75% level | Submittal of Completion of Evidence | Review of plan indicates benchmarks and targets are met | 100% | 100% | 100% | 100% | Debra Falkiner, Deidre Thomas-Murray | MSIP: 6.3.4 CSIP: 98
I.D.3.D | Develop and communicate an articulated plan of counseling services for students experiencing homelessness | 2011-11-14 | 2012-06-30 | Continue to provide wrap around services for by designing a counseling program for clientele | Determine optimum counseling services for students experiencing homelessness on a quarterly basis. | Monitor the processes for counseling services for students experiencing homelessness on a daily basis | Submittal of Completion of Evidence | Completion of program will be evidenced by submission of the final report. | 100% | 100% | 100% | 100% | Debra Falkiner, Deidre Thomas-Murray
I.D.4 | Strategy 4: Develop a Summer School program for students needing intervention, remrdaition acclreation while expanding offerings and options beyond summer school | 11/1212 | 2013-06-30 | Using the 1st benchmark assessment, plan student interventions at the district and/or school level that are immediate by means of SES and other after school programs | Ensure all elementary and middle schools have operational after school programs that meet the needs of its population | Investigate alternate plans for summer school and solidify plan for summer school by March 2013;continue onsite interventions based on formative assessment data | Submittal of Completion of Evidence | After school program evaluation and intervention session student data reflects student progress; alternate summer school designs completed | 100% | 100% | 100% | 100% | Sheila Smith Anderson | MSIP: 6.1.4 CSIP: 16
I.D.4.a | Audit summer courses offered in 2011-2012 and expand based on indicated needs | 2012-12-04 | 2013-01-04 | Design surveys for individual populations | Administer the surveys | Analyze results of surveys | Submittal of Completion of Evidence | Use analyzed results to develop alternate summer school offerings | 100% | 100% | 100% | 100% | Sheila Smith Anderso; Dan Edwards; Paula Knight, Rosemary Martin
I.D.4.b | Develop summer school plan by January 2013 | 2011-11-21 | 2013-03-30 | Examine evaluation of previous summer school program | Develop a plan for targeted populations of students | Distribute proposed plan to Academic Team and selected staff for feedback and possible plan revision | Submittal of Completion of Evidence | Complete summer school recruitment plan and roll out by March 2013 | 100% | 100% | 100% | 100% | Sheila Smith Anderson
I.E. | Objective E: The District will guarantee meaningful learning for students identified as gifted and/or performing beyond proficiency. . | 2011-10-01 | 2013-06-30 | Eligible students are identified and coded | Standardized data is screened and student identified as candidates for the gifted program | Candidates are contacted and assessed for gifted eligiblity | Submittal of Completion of Evidence | Students identified as eligible for gifted services are marked in SIS and schools are informed of students status by email | 100% | 100% | 100% |  | Michelle Jones, Sheila Smith-Anderson, | MSIP: 7.2.1, 7.2.2, 7.2.3 CSIP: 79-84
I.E.1. | Strategy 1: Monitor the developed processes to provide services for all identified gifted students | 2012-10-01 | 2013-06-30 | Monitor documentation process weekly to ensure all identified gifted students are coded correctly in SIS | Conduct reconciliation with technology to verify that all gifted students are identified within district data reports on the monthly basis | Ensure all gifted students are correctly coded by regularly screening gifted status on the quarterly basis | Submittal of Completion of Evidence | Eligible and Ineligible students status are updated in SIS and each school receives a GT-3 to insert into student permanent records. Gifted pull out teachers are also sent a copy of the students’ GT-3 and monthy class list updates. | 100% | 100% | 100% |  | Michelle Jones, Sheila Smith-Anderson, Curriculum Supervisors | MSIP: 7.2.1, 7.2.2, 7.2.3 CSIP: 79-84
I.E.1.b | Design program for underserved gifted students | 2011-09-01 | 2013-06-30 | Establish team to design program for underserved gifted students | Complete plan and begin initial implementation | Conduct program monitoring to ensure receipt of services occurs and adjustments made based on monitoring data | Submittal of Completion of Evidence | All SLPS students qualifying for gifted services enrolled in a school with gifted services. | 100% | 100% | 100% |  | Michelle Jones
I.F | Objective F: The District will review and restructure the guidance program. | 2009-10-09 | 2014-06-30 | Establish a team to develop a comprehensive guidance program by Fall 2009 | Design and implement a comprehensive guidance program by June 2011 | Monitor implementation of the comprehensive guidance program across the 2011-12 and 2012-13 & 14 school years | Submittal of Completion of Evidence | Comprehensive Guidance Manual, Curriculum and unit/lesson design, A+ Manual | 100% | 100% | 75% |  | Chip Jones, Tim Murrell, Sheila Smith-Anderson; Ira Bivens, Jim Dishman, Curriculum Supervisors, CTE specialists | MSIP: 6.9.1, 6.9.4 CSIP: 144, 145
I.F.1 | Refine the comprehensive guidance program and embed each of the DESE prescribed components with focus on program, curriculum and evaluation | 2009-10-01 | 2012-12-31 | Establish team to design guidance curriculum and create a first draft by Spring 2009 | Guidance curriculum objectives are included in existing social studies, science and PE curricula by December 31, 2012 | Constituent review team provides feedback on proposed curriculum and inclusion in existing curricula by June of 2014 | Submittal of Completion of Evidence | Components of guidance curriculum are implemented | 100% | 0% | 0% |  | Chip Jones; Tim Murrell; Sheila Smith Anderson; Curriculum Supervisors; CTE Specialists
I.G | Objective G :Require a data-driven connection between professional development expenditures and teacher and/or student performance. | 2012-08-01 | 2013-06-30 | Review and analyze current PD expenditures for staff by the end of Dec. 2012 | Complete a comparison between PD costs, staff attendance at PD, and student performance by Jan. 30, 2013. | Use the data obtained from comparison analysis for comprehensive PD planning for 2013-2014. | Submittal of Completion of Evidence | A PD plan for 2013-2014 reflecting the finds from the comparison analysis and future educational needs (i.e., CCSS). | 100% | 100% | 70% |  | Bertha Doar; Audrey Jackson; Sheila Smith-Anderson | CLRP: 30
I.H | Objective H: Provide supports for central office development of a comprehensive PD plan that aligns systemic goals and objectives with staff, student and teacher performance | 2012-10-01 | 2013-06-30 | Review current pd plan for comprehensive alignment to Accountability Plan by Jan. 2012 | Refocus components of pd not aligned to meet systemic goals of Accountability Plan by the end of 3rd quarter | Modify pd plan and establish training schedule for the 2013-2014 school year – June, 2013 | Submittal of Completion of Evidence | Prepare evaluation plan to determine alignment | 100% | 100% | 100% | 100% | Audrey Jackson; Sheila Smith-Anderson
I.H.1 | Require that assessment of professional development effectiveness be evidenced in part by documentation of identified changes in instructional practice | 2012-08-01 | 2013-06-30 | Review existing data regarding professional development - targeting critical need areas based on student data per IBD report regarding more PD through black out days by 1st quarter, 1st semester, 3rd quarter and 4th reporting period. | Analyze the number of participants, quality of sessions to determine areas needing improvement and align future professional development through the use of MyLearningPlan for 2013-2014 school year. | Provide training to teachers that addresses identified areas from MyLearningPlan analysis by May, 2013 | Submittal of Completion of Evidence | Provide evidence from student performance that professional development aligns directly to teacher needs | 100% | 100% | 100% | 100% | Audrey Jackson; Sheila Smith-Anderson | CLRP: 3, 16, 30
I.H.2 | Design and implement a comprehensive 2-year Beginning Teacher Assistance (BTAP) Mentoring Plan | 2012-08-01 | 2014-06-30 | Review current university BTAP support by the end of 1st semester. | Assign teacher mentors by the end of 1st semester. Communicate BTAP offerings with non-tenured teachers by the end of 1st semester. | Receive and file BTAP attendance information from non-tenured staff. Send reminders to non-tenured staff regarding BTAP requirement. | Submittal of Completion of Evidence | Provide evidence of implementation of revised SLPS BTA Mentoring Program | 100% | 100% | 100% | 100% | Sheila Smith-Anderson
| Action Steps | Start Date | End Date | 25% Benchmark (BM1) | 50% Benchmark (BM2) | 75% Benchmark (BM3) | 100% Benchmark (BM4) | Completion / Evidence | % Progress toward Benchmark Attainment |  |  |  | Owner | Cross-Reference
II | II. Highly Qualified Staff
II | GOAL: Recruit, develop and retain district employees who demonstrate the knowledge, skills and professional capacity required to guarantee student learning.
II.A | Objective A : The District will ensure that every position has a written job description delineating duties, functions, operating procedures and responsibilities. | 2012-07-01 | 6/31/13 | N/A | Audit all job titles and functions (job descriptions) District-wide and determine if job descriptions are current or obsolete. Completed by January 2013 | Post all current / updated job descriptions to www.slps.org Completed by January, 2013. | Submittal of Completion of Evidence | Electronic and Hard copies of current descriptions are on file in the Chief Human Resources Officers office. | 100% | 100% | 100% | 100% | James Henderson | CLRP: 8
II.B | Objective B: Recruit and hire Highly Qualified Staff in all academic areas. | 2012-07-01 | 6/31/13 | Develop a robust and aggressive recruitment plan/schedule – visiting colleges and universities: Illinois, Missouri, Arkansas, Mississippi, Tennessee, Indiana and Kentucky . Completion date: June, 2013 | Identify and train district administrators / generalists “recruitment teams” on teacher selection. Completion date: February, 2013 | - Rollout / implement the “recruitment calendar & recruitment plan”. Completion date: January , 2013 | Submittal of Completion of Evidence | Recuritment Plan, Training docuemnts / sign-in sheets; Recuritment Calendar. | 100% | 100% | 100% | 100% | James Henderson | CLRP: 21, 30
II.D | Implement Qualifiaction exams for support staff | 2012-08-01 | 6/31/13 | Identify and select on-line company to administer Support Staff Qualification Exams for ALL incoming support personnel. Completion Date: December, 2013. | - Develop & test prototypes of Support Staff Qualification Exams. Completion Date: December, 2013 | Select the ”Final Versions” of the Support Staff Qualifiaction Exams, and develop a “rollout plan” for the 2013 – 2014 School year. Completion Date: January, 2013 | Submittal of Completion of Evidence | Support Staff Qualification Exams Approved for use and protoytpes are on file in the Human Resources office. EOY Report (targets & successful attainment of targets). | 100% | 100% | 100% | 100% | James Henderson
| Action Steps | Start Date | End Date | 25% Benchmark (BM1) | 50% Benchmark (BM2) | 75% Benchmark (BM3) | 100% Benchmark (BM4) | Completion / Evidence | % Progress toward Benchmark Attainment |  |  |  | Owner | Cross-Reference
III | III. Facilities, Instructional Resources, Support
III | Goal: To ensure the District’s full accreditation through the provision of a physical environment and supporting programs and processes that guarantee student learning.
III.A | The District will develop a secure technological environment that effectively and efficiently integrates curriculum, instruction and assessment to improve data collection, analysis, reporting and decision-making that positively impact classroom instruction | 2012-08-01 | 2014-06-30 | Create, post, and review RFP for upgrade to current infrastructure | - Submit appropriate documentation for e-Rate submission to SLD & Board | Work with selected vendor to order and install equipment / Maintenance of equipment on an on-going basis | Submittal of Completion of Evidence | Provide evidence of school/student information management system development, implementation and expansion | 100% | 100% | 100% | 100% | Cheryl VanNoy
III.A.2 | Strategy 2:Implement a district-wide student information management system | 2012-08-01 | 2012-06-30 | Assess need of Prop S computer labs at each elementary | Prepare for wiring/power needs, order equipment and furniture | Installation of Prop S labs / Maintenance of equipment on an on-going basis | Submittal of Completion of Evidence | Provide evidence of school/student information management system development, implementation and expansionnformation management system development, implementation and expansion | 100% | 65% | 90% | 95% | Cheryl VanNoy
III.B | The District will provide a climate for all students, staff, and visitors that is safe, secure and conducive to teaching, learning and classroom management. | 2012-07-01 | 2013-06-30 | Successful completion of Strategy 1 | Successful completion of Strategy 2 | N/A | Submittal of Completion of Evidence | See Completion of Evidence for Strategy 1 (III B 1). See Completion of Evidence for Strategy 2 (III B 2) | 100% | 100% | 100% | 100% | Lisa Taylor; David E. Glenn, Sr.; and Misty Dobynes
III.B.1 | Strategy 1: The District's Emergency Management Committee and Building Principals will update the District's/Schools' Emergency Operations Plans. | 2012-07-01 | 2013-06-30 | School administrators or designee, will elect members for the Emergency Management Committee prior to the end of the 1st quarter. | Team members will participate in Federal Emergency Management Agency (FEMA) and National Incident Management System (NIMS) web-based training by February 15, 2013. | Revise, approve, and monitor the rollout Schools & District emergency operations plans by December 21, 2012. | Submittal of Completion of Evidence | Submit documentation supporting all training completed for 2012/2013 School Year | 100% | 100% | 100% | 100% | Lisa Taylor; David E. Glenn, Sr.; and Misty Dobynes
III.B.2 | Strategy 2: Provide professional development training to safety and security staff. | 2012-08-06 | 2013-06-30 | Establish and create a training plan detailing the training to be provided to the school safety & security personnel for the 2012/2013 school year. | Provide and monitor ongoing training throughout the school year. | Submit an analysis of the quarterly reports | Submittal of Completion of Evidence | Provide Emergency Operation Plans for every school. Copies are kept in the Safety & Security Department available for review. | 100% | 100% | 100% | 100% | Lisa Taylor; David E. Glenn, Sr.; and Misty Dobynes
III.C | Objective C: [Facilities]: The District will provide facilities which are safe, secure and conducive to teaching and learning. | 2011-07-01 | 2013-06-30 | Implement Preventive/Corrective work order system (ISIS/Pro) | Conduct Monthly Joint Review | Conduct Monthly Joint Review | Submittal of Completion of Evidence | Monthly Joint Review documents will be used to monitor progress via ISIS/Pro databank. These MJR reports are kept in the Operations Department office | 100% | 100% | 100% | 100% | Roger CayCe; Team: Yvonne Green; Larry Brown; Rosmon Johnson | CLRP : 7
III.C.1 | Strategy 1: The District will ensure that all facilities are maintained to meet local, state and national safety codes. | 2011-07-01 | 2013-06-30 | Conduct monthly and yearly safety code joint reviews | Document that 50% of facilities meet safety codes | Document that 75% of facilities meet safety codes | Submittal of Completion of Evidence | Provide copies from various vendors doing the inspections that safety codes and compliances were completed for all facilities. Copies of all inspections are kept in the Operations Department. | 100% | 100% | 100% | 100% | Roger CayCe: Yvonne Green; Larry Brown; Rosmon Johnson
III.C.1.a | Action Step A: Complete 3-year AHERA re-inspection update | 2011-07-01 | 2013-06-30 | Retain environmental company | 50% of the sites have been re-inspected and all changes have been updated as required | 75% of the sites have been re-inspected and all changes have been updated as required. | Submittal of Completion of Evidence | Provide documentation that inspections were completed at all school sites | 100% | 100% | 100% | 100% | Yvonne Green; Roger CayCe; Mike Dobbs
III.C.2 | The District will ensure that all Proposition S funds approved for projects to improve academic performance; ensure a safe, secure environment; promote a healthy lifestyle for students and staff | 2011-07-01 | 2013-10-31 | Design phase completed for Phase II Projects | Bids posted and received and SAB approval of Phase II Projects | Construction started/ Substantial Completion of Phase II projects | Submittal of Completion of Evidence | Completion of projects, Close out documentation i.e.; certified As- Build- Drawings, O&M manuals, certifications. Also, pictures of completed projects | 100% | 100% | 80% | 60% | Roger CayCe; Team: Yvonne Green; Rosmon Johnson; Mike Dobbs; Ron Roberts
III.D | Objective D: [Finance]: The District will manage spending by aligning revenues and expenditures to Accountability Plan. | 2012-08-13 | 2013-06-30 | Identify all revenue sources with estimates of ensuing year revenues | Conduct meetings and workshops to identify and prioritize district programs and initiatives | Develop funding scenarios which incorporate the prioritization of district programs and initiatives | Submittal of Completion of Evidence | FY14 Revenue & Expenditure Budget Projections which reflect a balanced budget | 80% | 60% | 60% |  | Leon Fisher | CLRP: 7
III.D.1 | Strategy 1: To develop and institute a formal month-end close process by Q4 of FY 2013. | 2012-08-13 | 2013-06-30 | SAP Reporting Module Assessment/Training for Finance Staff. | Development of detailed process flows by functional area | Execution of Month-End Close process with minimal errors and/or rework | Submittal of Completion of Evidence | Preparation/Distribution of Monthly Financial Statements (Balance Sheet and Income Statement) by July 2013 | 100% | 40% | 75% |  | Leon Fisher
III.D.3 | Strategy 3: The District will develop a Communications Plan whereby which to communicate results of District financial operations to external stakeholders | 2012-08-13 | 2013-06-30 | Develop document requirements | Standardize document formats | Update website | Submittal of Completion of Evidence | Electronic presentation of standard district financial documents to include: Adopted Budget Document , CAFR, and External Audit. | 100% | 90% | 50% |  | Leon Fisher
III.D.4 | Strategy 4: The District will establish a Finance Committee for the review and/revision of financial policies and guidance during the budget planning process | 2012-08-13 | 2013-06-30 | Develop fund balance policy | Develop investment policy | Develop the Internal Audit Plan | Submittal of Completion of Evidence | Review/Revise all financial policies on an annual basis. | 100% | 100% | 100% | 100% | Leon Fisher
III.F | Objective F: [Other Support Services]: The District will provide timely, effective and efficient transportation services to ensure on time arrival at school is 93%. | 2012-07-01 | 2013-06-28 | Have discussion with transportation vendor to set expectations | Analyze arrival data; report GPS on a daily basis | Adjust routes and schedules when chronic on time performances by routes are not met. | Submittal of Completion of Evidence | Provide evidence of expectations met through the GPS report | 100% | 50% | 75% | 100% | Deanna Anderson; Toyin Akinola | CLRP:7
III.F.1 | Strategy 1: The District will provide appropriate number of buses that maximizes the usage without compromising safety. Cost per student should = $10. | 2012-07-01 | 2013-06-30 | Document number of buses and route schedules used for daily transport. Present fall routes to the Board by October 1. | Develop and monitor route costs and remove ghost stops. Adjust where appropriate. | Conduct monthly monitoring of process to maximize transportation efficiencies. | Submittal of Completion of Evidence | Produce a final report that identifies cost per child associated with buses and scheduling along with number of bus routes throughout the year. | 100% | 50% | 75% | 100% | Deanna Anderson; Toyin Akinola
III.G | Objective G: [Other Support Services]: The District will maintain a 56 %or above participation rate for breakfast and maintain a 78% or above participation rate | 2011-08-01 | 2013-06-30 | By the 1st day of school establish systemic targets and share with the SAB | During the 1st quarter develop and rollout the process for monitoring participation rates on a daily basis | Maintain a monthly reporting system and Generate Quarterly Breakfast & Lunch Participation Reports | Submittal of Completion of Evidence | Generate Fiscal year End breakfast and lunch participation rate which reflects the successful attainment of the Breakfast particpation rate ( >= 56%) and Lunch Partcipation (>= 78% ) for FY 2012 - 2013 | 100% | 100% | 100% |  | Althea Santiago; Team: George Nash, Tenecia Williams, and Stephanie Honeywood
III.G.1 | Strategy 1: Promote a healthy meal program in a safe and appealing school cafeteria environment | 2012-10-01 | 2013-06-30 | Survey school sites about meal programs and generate reports (results of the surveys) prior to the mid-point of the 1st quarter | Analyze reports to identify opportunities for improvement (i.e. school low application percentage) Prior to the beginning of the 2nd Quarter | Implement the recommendations of the reports and surveys at the beginning of the 2nd Quarter and monitor the progress (via monthly reports) during the school year | Submittal of Completion of Evidence | Generate Fiscal Year end "Opportunities for Improvement Reports" which reflect the improvement in meal programs for Fiscal Year 2012 - 2013 | 100% | 100% | 100% |  | Althea Santiago; Team: George Nash and Stephanie Honeywood
III.G.1.a | Action Step A: Obtain from parents/families a free and reduced meal application or have a direct certified status for 98% of students enrolled in schools where the district is responsible for providing meal service. | 2011-08-16 | 2013-06-30 | Determine goals to be obtained based on application returns prior to the end of September | Set goals for each school site and communicate to schools Prior to the beginning of October | Monitor the process (via status reports) of reviewing application reports, identify positive or negative status, and assist the schools in remedying any negative application status during the school year | Submittal of Completion of Evidence | Generate Fiscal Year end "Application Completion Reports" which reflect the successful completion rate (=> 98%) for Fiscal Year 2012 - 2013 | 100% | 100% | 100% |  | Althea Santiago; George Nash
| Action Steps | Start Date | End Date | 25% Benchmark (BM1) | 50% Benchmark (BM2) | 75% Benchmark (BM3) | 100% Benchmark (BM4) | Completion / Evidence | % Progress toward Benchmark Attainment |  |  |  | Owner | Cross-Reference
IV. | IV. Parent and Community Involvement - Policy # 1230
IV | Goal: The District will recognize and adopt the goals of the SAB approved policy #1230 that commits to making the parent/family and the community a part of the education process of students
IV.A | Objective A: The District will create awareness of and provide access for all stakeholders (parents, district staff and community) to internal and external resources and training designed to improve student achievement | 2012-07-01 | 2013-06-30 | Full completion of the first quarter calendar/timeline tasks | Full completion of the second quarter calendar/timeline tasks | Full completion of the third quarter calendar/timeline tasks | Submittal of Completion of Evidence | Documentation of completion. | 100% | 100% | 100% | 100% | Stacey Clay; Jeffrey Rhone | CLRP: 11, 4, 25, 5, 6, 10, 4
IV.B | Objective B: Build capacity for effective partnerships with stakeholders, designed to improve student achievement | 2011-07-01 | 2013-06-30 | 10% increase in PTO participation over 2010-11 | 10% increase in volunteer service hours | Increase in parent attendance at family academic nights | Submittal of Completion of Evidence | B1. Comparison of parent enrollment and attendance at PTO meetings: B2. Increase on school volunteer hours logged compared to 2011-12: B3. Increase in parent attendance at family academic nights | 100% | 100% | 100% | 100% | Stacey Clay; Jeffrey Rhone
| Action Steps | Start Date | End Date | 25% Benchmark (BM1) | 50% Benchmark (BM2) | 75% Benchmark (BM3) | 100% Benchmark (BM4) | Completion / Evidence | % Progress toward Benchmark Attainment |  |  |  | Owner | Cross-Reference
V. | Governance
V | Goal: The District will guarantee academic improvement, and patron satisfaction by providing effective managerial leadership and meaningful governance representation, focused on student learning to regain accreditation
V.B | Objective B: SLPS administration and the SAB will implement a continuous monitoring system through which the administration can provide the board with a data-informed, evidence-based assessment of Accountability Plan execution | 71/2012 | 2013-06-30 | Develop a performance-based monitoring process prior to the 1st day of School | Share components of monitoring process with administration Prior to the end of September | Implement the Monitoring System prior to the 1st day of October. Monitor and manage the system though the end of FY 2011 - 2012 | Submittal of Completion of Evidence | Monitoring System Process is documented. Outputs of the monitoring system Draft of End of Year 2 Report is generated. | 100% | 100% | 100% | 100% | Stacey Clay Kelvin Adams; SAB
V.A.I | Strategy 1: Set timeline for staff to provide status report to the SAB and community | 2012-09-01 | 2013-06-11 | Prior to the end of September the Team Leaders will identify Timeline (Schedule) of individual Team Status meetings. | Prior to the end of each month Owners & PMO will update scorecards (Status Reports) on the PMO Portal | Prior to the 1st of every Month the PMO will provide monthly updates on each objective in the plan to the Team Leaders, Supt & SAB | Submittal of Completion of Evidence | End of Year 2 Report (Successes and Challenges is finalized and presented to the Supt & SAB | 100% | 100% | 100% | 75% | Stacey Clay Kelvin Adams; SAB
V.E | Objective E: SAB to participate in ongoing professional development focused on improving student achievement through the informed use of the board's governing documents | 2011-09-01 | 2012-06-30 | Board to participate in ongoing MSBA PD related to governance | Participation in ongoing PD sessions | Show evidence of session participation in discussion with district superintendent | Submittal of Completion of Evidence | Completion of PD sessions on governance |  |  |  |  | Stacey Clay Kelvin Adams; SAB
| Action Steps | Start Date | End Date | 25% Benchmark (BM1) | 50% Benchmark (BM2) | 75% Benchmark (BM3) | 100% Benchmark (BM4) | Completion / Evidence | % Progress toward Benchmark Attainment |  |  |  | Owner | Cross-Reference
V. | Superintendent Initiatives
FSS | Superintendent Initiative: Full Service Schools | 2012-09-01 | 2013-08-01 | Secure funding that ensures continued operation of the 10 schools through the current school year and beyond. Analyze existing MOUs and recommend continuation contingent upon ending date of each. | Strengthen the implementation, management, and monitoring of the Full Service model in 10 schools. | Conduct end-of-year analysis and create end-of-year report. | Submittal of Completion of Evidence | Show evidence of program operation and service delivery through the nFocus data collection system | 100% | 60% | 100% | 50% | Kelvin Adams, John Windom,
ICS | Superintendent's Initiative: Innovative Concept School | 2009-09-01 | 2012-06-30 | Approval by SAB for creation of high school geared specifically to high school dropouts | Approved vendor begins high school | Evidence that high school is operational and supports its mission of reducing dropouts | Submittal of Completion of Evidence | Evidence that high school is operational, matriculates and maintains at risk students with high attendance, low suspension and no expulsion | 100% | 100% | 75% |  | Kelvin Adams; Judge Jimmie Edwards; Debra Falkiner
PS | Superintendent's Initiative: Pilot Schools | 2012-09-01 | 2013-06-30 | Generate 3yr Student data report and analyze increase in student / school performance. | Generate End of 1st semester report and analyze increase in student / school performance. | Generate End of 2nd semester report and analyze increase in student / school performance. | Submittal of Completion of Evidence | Evidence of change from 2011-12 to 2012 -2013 as noted by improved attendance and performance on assessments, lower discipline | 100% | 100% | 100% | 100% | Kelvin Adams; Alice Roach