Full Service Schools

Goal

To develop Community Education sites into Full Service Schools (FSS)

Rationale

Full Service Schools will partner/collaborate with District and community service providers to respond to the academic, health, social and cultural developmental needs of SLPS students and their families.

Benefits

- Students achieving at higher academic levels

- Students having a wider range of opportunities to be engaged in wholesome developmental activities

- Enhanced focus on the development of the whole child

- Wiser use of diminishing community resources

- More readily accessible supports available to students, their parents, and community members

- Greater parent and community involvement

- Aligns with and supports the District’s Long Range Plan, particularly in the areas of Student Performance and Parent and Community Development

The Process

- Discuss with key stakeholders possible options for service delivery in light of funding reduction

- Reach agreement on new service delivery model

- Reduce community education centers from 16 to 13

- Vacate all community education coordinator and specialist positions

- Hire 13 community collaborative specialists

- Provide professional development to specialists, CEC principals, and council members centered on FSS

- Discuss Full Service Schools model with District and community partners/collaborators

- Conduct asset mapping in each CEC region

- Conduct needs survey in each CEC region

- Analyzation of asset mapping and needs survey results by each council

- Programs/services prioritized by each council

- Reconvene partners/collaborators to match needs with resources

- Seek additional funding to respond to situations where service providers are unable to assist

- Develop comprehensive FSS plans at each center

- Continue professional development for key stakeholders

- Assure day school plans incorporate FSS programs/services

- Review readiness of FSS implementation plans

- Share plans at Chairpersons’ meeting

- Implement FSS plans

- CEC’s open as Full Service Schools

- Continuous Improvement Process initiated

- Achievement status of Continuous Improvement goals periodically posted on District website

Time Line/Activities

August-September, 08	Agreement reached with key stakeholders regarding Full Service Schools model

September-December, 08	    Vacated positions

    Hired Staff

    In-serviced key stakeholders

    Conducted asset mapping in each region

    Conducted needs survey in each region

    Continued normal programming

January-May, 09	    Analyze needs survey data

    Match needs with assets in each region

    Reconvene District and community service providers

    Create Full Service School Plan for each center

    Seek funding and additional support where needed

    Continue normal programming

June-August, 09	    Conduct summer programs

    Continue readiness for FSS opening

September, 09	    Implement Full Service School concept

Budget

- District-wide multi-application software for tracking the academic progress of After School students, Councils, Volunteers, and other data needs

(Negotiations underway to lower one time cost)

- Annual software maintenance contract

(Negotiations underway to lower yearly licensing agreement cost)

$133,366

$37,646