Project Scheduling Guidelines

- Guidelines

This high-level guidance document is designed to help the project manager develop a well thought through and accurate project schedule. A good project schedule has detail sufficient for control by the project manager. It should not require excessive effort to maintain, especially on small, short time frame projects. A good schedule should incorporate the following: - Structure the project - determine activity categories - Look at whatever information you have about the project that you are planning. - Gather information from prior projects and from other project managers. - Identify or define the project goals, objectives, and scope. - Break down major activities into tasks and sub-tasks required to accomplish the activity. - Depending on the complexity of the task, these steps or subtasks can be further broken down. - The number of levels depends upon the size and complexity of the project. - The process of defining steps should continue until you are certain all major steps are included and accurate cost/hour estimates applied to the lowest level or activity. - The lowest task linked to a well-defined deliverable.